## Project Plan Template
[5 empty] | Planned |  | Completed |  | Slipped |  | Milestone | ◊
| Project Plan action items | Action Owner | Due Date | Dependency | week 1 | week 2 | week 3 | week 4 | week 5 | week 6 | week 7 | week 8 | week 9 | week 10 | week 11 | week 12 | week 13 | week 14 | week 15 | week 16 | week 17 | week 18 | week 19 | week 20
1 | Plan – Funding, Procurement and Demand and Capacity Modelling | initials | dd/mm/yy | no.of action
1.1 | Has FeNO product funding been agreed? If so, confirm the source
1.2 | If no additional funding, where will funding come from?
1.3 | You may need to consider and complete a business case to justify spend and to Ensure sustainability
1.4 | Ensure procurement process meets NHS Guidelines
1.5 | Secure product supply by choosing and engaging with approved supplier - Nobreath by Bedfont or NIOX VERO by Circassia https://wessexahsn.org.uk/projects/412/feno-products
1.6 | Consider potential demand and model capacity using available data (This may be achieved using case finding tools, or existing system searches to find your target patient group https://wessexahsn.org.uk/projects/423/help-with-identifying-your-patients-system-searches-and-prevalence-data)
1.7 | Agree staffing model to deliver the service
1.8 | Ensure required skills and competencies have been defined
1.9 | Secure sufficient staffing capacity in line with predicted activity (demand and capacity model)
1.1 | If staff numbers are insufficient, consider alternative workforce arrangements; recruitment, secondment, alternate but appropriate clinical support e.g. pharmacists
2 | Plan – Delivery Model
2.1 | Review current pathway then develop and agree delivery model. What is the optimum model to ensure full coverage across target population?
2.2 | Develop a consistent Framework of Clinical Approach, including points of patient escalation/referral, using AAC materials
2.3 | Discussion with Quality and Equality Service Lead to ensure model considers inclusion of all
2.4 | Discussion with relevant community groups and third sector partners to improve access to service
2.5 | Develop a Standard Operating Procedure based on agreed clinical framework to ensure consistency of approach. To include (not exhaustive):
2.6 | Clear referral process or, agreed target group
2.7 | Patient communications https://wessexahsn.org.uk/projects/425/patients-communications
2.8 | Escalation/referral process, if required
2.9 | Clinical Governance/review arrangements.
3 | Plan – Communications, Digital and IT
3.1 | Development (procurement) of Patient Information Pack (including overview of FeNO)
3.2 | Availability of above in different formats and languages to meet physical and cultural needs
3.3 | Link with Communications leads to promote and raise awareness of the FeNO pathway, if required
3.4 | Does your EPR system that allows you to document FeNO results (check newly developed Ardens template)
4 | Plan – Reporting/Evaluation
4.1 | How will you collect and share your data (check newly developed Ardens template), review reporting template at https://wessexahsn.org.uk/projects/424/managing-the-change-process-from-implementation-to-reporting and arrange for data to be submitted to the AAC
4.2 | Do you have a member of the team responsible for collecting FeNO data, summarising staff and patients’ comments, reviewing and acting on the findings?
4.3 | Have you thought about how you might create a case study to share learning and understand areas for improvement?
5 | Do – Implement your model
5.1 | Select team (assign roles/tasks).
5.2 | Ensure process/pathways are in place
5.3 | Ensure plan is communicated
5.4 | Ensure FeNO training has been completed (product suppliers can provide training) https://wessexahsn.org.uk/projects/422/education-toolkit
5.5 | Ensure FeNO products have been received and are ready to deploy
5.6 | Ensure appropriate infection control processes are in place and understood https://wessexahsn.org.uk/projects/449/infection-control
5.7 | Ensure all staff can update patient records
5.8 | Ensure FeNO Ardens template can be utilised
6 | Learning
6.1 | Convene team meeting to review:
6.2 | Any immediate issues identified?
6.3 | What has worked well and what requires improvement? For example, are FeNO products being used correctly, are there any additional training needs, do patients understand the process?
6.4 | Do you have any staff/patient feedback?
6.5 | Are you testing patients who match the eligibility criteria?
6.6 | Do the numbers match the predictive modelling?
7 | Sustainability
7.1 | Does the FeNO service have clear leadership and plans for ongoing delivery?
7.2 | Do you have clear governance arrangements in place?
7.3 | Have you thought about whether the FeNO service can be adapted to meet other conditions/needs?
7.4 | Have you identified funding and staffing requirements?
8 | Refine
8.1 | Alter delivery model to reflect lessons learned
8.2 | Refresh staff training to include new information gathered from the process so far
8.3 | Review clinical deployment to ensure needs are met.